## Sheet1
Notes : You need to update the timeline on the right to reflect the current dates. Tasks must be assigned to one (and only one) owner, and each owner must have a different color associated with them (it cannot be red or green). Each requirement from the requirements document should be included, and referenced by number. You should also include any other tasks that will take time (setup, testing, documentation, etc). Each "day" on the calendar represents 2 hours of work. You should break down your tasks into chunks of 1-4 "days". The tasks below are for demonstration purposes only - replace them with your requirements and tasks. The yellow bars on the calendar represent weekends - you probably want to take those (and any breaks) into account while planning!
[6 empty] | September |  |  |  |  | October | [30 empty] | November | [29 empty] | December
Requirement # | Requirement | Task # | Task | Estimate | Owner | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06
1 | Back-End | 1.1.1 | Setup Spring Workspace | 2 | Amol
|  | 1.1.2 | Setup and Create MongoDB connections | 1 | Sumantra
|  | 1.1.3 | Create Repository/ DAO classes | 5 | Abhinav
|  | 1.1.4 | Create Models, Views and Controllers | 1 | Abhinav
|  | 1.1.5 | Add Logging Utility | 2 | Amol
|  | 1.1.6 | Client Sign-up and email Verification API | 3 | Amol
|  | 1.1.7 | Client Profile API - Create | 3 | Amol
|  | 1.1.8 | Client Profile API - Get | 2 | Amol
|  | 1.1.9 | Client profile API - Update | 2 | Sumantra
|  | 1.1.10 | Coach Sign-Up API | 3 | Sumantra
|  | 1.1.11 | Coach Profile API - Create | 3 | Amol
|  | 1.1.12 | Coach Email Verification | 3 | Abhinav
|  | 1.1.13 | Coach Verification API (By Admin) | 3 | Abhinav
|  | 1.1.14 | Coach Profile API - Get | 3 | Abhinav
|  | 1.1.15 | Coach Profile API - Update | 2 | Abhinav
|  | 1.1.16 | Client/Coach/Admin Sign-In API (JWT) | 4 | Amol
|  | 1.1.17 | Fixing Login Sign-up Bugs | 3 | Amol, Abhinav, Sumantra
|  | 1.1.18 | View All Coach API | 3 | Amol
|  | 1.1.19 | Client - add/remove Coach API | 3 | Amol
|  | 1.1.20 | Client - add/ Update Goal API | 3 | Sumantra
|  | 1.1.21 | Client - Get all Goals API | 2 | Sumantra
|  | 1.1.22 | Client - Get Personalized Content | 3 | Sumantra
|  | 1.1.23 | Coach - Get all clients API | 3 | Abhinav
|  | 1.1.24 | Coach - Get All Goals for Client API | 2 | Abhinav
|  | 1.1.25 | Coach - Add Comments for Client Meetings API | 3 | Abhinav
|  | 1.1.26 | Admin - Approve Coach API | 3 | Sumantra
|  | 1.1.27 | Admin - Update/ Delete Client Profile API | 5 | Sumantra
|  | 1.1.28 | Admin - Get All Coach/Client API | 3 | Abhinav
|  | 1.1.29 | Add Swagger Documentation | 3 | Amol
|  | 1.1.30 | Testing - Client APIs | 1 | Amol
|  | 1.1.31 | Testing - Coach APIs | 1 | Abhinav
|  | 1.1.32 | Testing - Login API | 1 | Sumantra
|  | 1.1.33 | Fixing Bugs | 6 | Amol, Abhinav, Sumantra
|  | 1.1.34 | Deployment to Cloud - AWS | 3 | Sumantra
2 | Database | 2.1. | Create Static Tables (Roles, Tags) | 2 | Sumantra
|  | 2.2 | Add Tags Provided By Client | 2 | Abhinav
|  | 2.3 | Add Personalized Content Provided By Client | 2 | Amol
|  | 2.4 | Database Deployement | 3 | Sumantra
|  | 2.5 | Develop Databse Queries | 3 | Sumantra
1.2 | Front-End
Setup
|  | 1.1 | Setup - CRA | 1 | Rahul Sharma
|  | 1.2 | Setup - Tailwind CSS & Material CSS | 1 | Rahul Sharma
|  | 1.3 | Setup- Webpack & Node SASS | 1 | Rahul Sharma
|  | 1.4 | React - Browser Rotuing & Private Routes | 2 | Rahul Sharma
|  | 1.5 | Redux API service Layer + Redux Thunk | 2 | Rahul Shahi
|  | 2 | Landing Page UI
|  | 2.1 | Generic Nav + Action Buttons | 2 | Rahul Shahi
| Week 1 Deliverable | 2.2 | Main Content UI | 2 | Rahul Shahi
|  | 2.3 | Login/Signup Wizard | 2 | Rahul Shahi
|  | 2.4 | Email Verification flow | 1 | Rahul Sharma
|  | 2.5 | Generic Footer UI + Landing Responsive Design | 2 | Rahul Shahi
|  | 3.1 | About Page UI | 1 | Rahul Sharma
|  | 4 | Survey Form
|  | 4.1 | React formik setup | 2 | Rahul Sharma
| Week 2 Deliverable | 4.2 | Client survey form | 3 | Rahul Sharma
|  | 4.3 | Coach survey form | 2 | Rahul Sharma
|  | 4.4 | Redux generic store form handling | 1 | Rahul Sharma
|  | 5 | Client Dashboard
|  | 5.1 | Client Profile Tab UI + Generic Dashboard Nav | 1 | Rahul Shahi
|  | 5.2 | Client goal progress component
|  | 5.2.1 | Individual progress | 1 | Rahul Shahi
|  | 5.2.2 | Overall progress | 1 | Rahul Shahi
|  | 5.3 | Dashboard action tab setup + code splitting + Private Routing | 1 | Rahul Shahi
|  | 5.4 | Personalised Content
|  | 5.4.1 | Content Card
| Week 3 Deliverable | 5.4.1.1 | Content Thumbnail + tag pills + metadata wrapping | 3 | Rahul Shahi
|  | 5.4.1.2 | Content Card Pagination UI | 1 | Rahul Shahi
|  | 5.5 | Coach Tab UI
|  | 5.5.1 | Personal Coach Card + Calendly Integration | 3 | Rahul Sharma
|  | 5.5.2 | All Coach UI generic card | 2 | Rahul Sharma
|  | 5.6 | Goal Updates Tab UI
| Week 4 Deliverable | 5.6.1 | All goal list | 2 | Rahul Shahi
|  | 5.6.2 | Add goal form | 2 | Rahul Shahi
|  | 5.6.3 | Edit Goal form | 2 | Rahul Sharma
|  | 5.6.4 | Individual Goal Display UI | 2 | Rahul Sharma
|  | 5.6.5 | Goal Stage wizard | 1 | Rahul Sharma
|  | 6 | Coach DashBoard
|  | 6.1 | Coach routing setup + Redux coach store setup | 2 | Rahul Shahi
| Week 5 Deliverable | 6.2 | Coach Client list UI | 3 | Rahul Shahi
|  | 6.3 | Individual Client detail UI | 3 | Rahul Shahi
|  | 6.4 | Coach Client goal wizard | 2 | Rahul Sharma
|  | 6.5 | Coach meeting notes wizard | 2 | Rahul Sharma
|  | 7 | Admin Dashboard UI
| Week 6 Deliverable | 7.1 | Admin routing setup + Redux admin store setup | 1 | Rahul Sharma
|  | 7.2 | All Coach UI | 2 | Rahul Sharma
|  | 7.3 | Coach action wizard | 1 | Rahul Sharma
|  | 7.4 | All Client UI | 2 | Rahul Shahi
|  | 7.5 | Client action wizard | 1 | Rahul Shahi
| Week 7 Deliverable | 8 | Dev Testing + Bug fix | 4 | Rahul Shahi + Rahul Sharma
Amol
Abhinav
Sumantra
Rahul Shahi
Rahul Sharma