## Project Plan
Notes : You need to update the timeline on the right to reflect the current dates. Tasks must be assigned to one (and only one) owner, and each owner must have a different color associated with them (it cannot be red or green). Each requirement from the requirements document should be included, and referenced by number. You should also include any other tasks that will take time (setup, testing, documentation, etc). Each "day" on the calendar represents 2 hours of work. You should break down your tasks into chunks of 1-4 "days". The tasks below are for demonstration purposes only - replace them with your requirements and tasks. The yellow bars on the calendar represent weekends - you probably want to take those (and any breaks) into account while planning!
[6 empty] | September |  |  |  |  | October | [30 empty] | November | [29 empty] | December
Requirement # | Requirement | Task # | Task | Estimate | Owner | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06
1 | Back-End | 1.1.1 | Setup Spring Workspace | 2 | Amol
|  | 1.1.2 | Setup and Create MongoDB connections | 2 | Sumantra
|  | 1.1.3 | Create Repository/ DAO classes | 5 | Abhinav
|  | 1.1.4 | Create Models, Views and Controllers | 1 | Abhinav
|  | 1.1.5 | Add Logging Utility | 2 | Amol
|  | 1.1.6 | Client Sign-up and email Verification API | 3 | Amol
|  | 1.1.7 | Client Profile API - Create | 3 | Amol
|  | 1.1.8 | Client Profile API - Get | 2 | Amol
|  | 1.1.9 | Client profile API - Update | 2 | Sumantra
|  | 1.1.10 | Coach Profile Add | 3 | Sumantra
|  | 1.1.11 | Coach Sign-Up API | 3 | Amol
|  | 1.1.12 | Coach Email Verification | 3 | Abhinav
|  | 1.1.13 | Coach Verification API (By Admin) | 3 | Abhinav
|  | 1.1.14 | Coach Profile API - Get | 3 | Abhinav
|  | 1.1.15 | Coach Profile API - Update | 2 | Abhinav
|  | 1.1.16 | Client/Coach/Admin Sign-In API (JWT) | 4 | Amol
|  | 1.1.17 | Fixing Login Sign-up Bugs | 3 | Amol, Abhinav, Sumantra
|  | 1.1.18 | View All Coach API | 3 | Amol
|  | 1.1.19 | Client - add/remove Coach API | 3 | Amol
|  | 1.1.20 | Client - add/ Update Goal API | 3 | Sumantra
|  | 1.1.21 | Client - Get all Goals API | 2 | Sumantra
|  | 1.1.22 | Client - Get Personalized Content | 3 | Sumantra
|  | 1.1.23 | Coach - Get all clients API | 3 | Abhinav
|  | 1.1.24 | Coach - Get All Goals for Client API | 3 | Sumantra
|  | 1.1.25 | Coach - Add Comments for Client Meetings API | 3 | Abhinav
|  | 1.1.26 | Admin - Approve Coach API | 3 | Sumantra
|  | 1.1.27 | Admin - Update/ Delete Client Profile API | 5 | Sumantra
|  | 1.1.28 | Admin - Get All Coach/Client API | 3 | Abhinav
|  | 1.1.29 | Add Swagger Documentation | 3 | Amol
|  | 1.1.30 | Testing - Client APIs | 1 | Amol
|  | 1.1.31 | Testing - Coach APIs | 1 | Abhinav
|  | 1.1.32 | Testing - Login API | 1 | Sumantra
|  | 1.1.33 | Fixing Bugs | 6 | Amol, Abhinav, Sumantra
|  | 1.1.34 | Deployment to Cloud - AWS | 3 | Sumantra
2 | Database | 2.1. | Create Static Tables (Roles, Tags) | 2 | Sumantra
|  | 2.2 | Add Tags Provided By Client | 2 | Abhinav
|  | 2.3 | Add Personalized Content Provided By Client | 2 | Amol
|  | 2.4 | Database Deployement | 3 | Sumantra
|  | 2.5 | Develop Databse Queries | 3 | Sumantra
1.2 | Front-End
Setup
|  | 1.1 | Setup - CRA | 1 | Rahul Sharma
|  | 1.2 | Setup - Tailwind CSS & Material CSS | 1 | Rahul Sharma
|  | 1.3 | Setup- Webpack & Node SASS | 1 | Rahul Sharma
|  | 1.4 | React - Browser Routing & Private Routes | 2 | Rahul Sharma
|  | 1.5 | Redux API service Layer + Redux Thunk | 2 | Rahul Shahi
|  | 2 | Landing Page UI
|  | 2.1 | Generic Nav + Action Buttons | 2 | Rahul Shahi
| Week 1 Deliverable | 2.2 | Main Content UI | 2 | Rahul Shahi
|  | 2.3 | Login/Signup Wizard | 2 | Rahul Shahi
|  | 2.4 | Email Verification flow | 1 | Rahul Sharma
|  | 2.5 | Generic Footer UI + Landing Responsive Design | 2 | Rahul Shahi
|  | 3.1 | About Page UI | 1 | Rahul Sharma
|  | 4 | Survey Form
|  | 4.1 | React formik setup | 2 | Rahul Sharma
| Week 2 Deliverable | 4.2 | Client survey form | 3 | Rahul Sharma
|  | 4.3 | Coach survey form | 2 | Rahul Sharma
|  | 4.4 | Redux generic store form handling | 1 | Rahul Sharma
|  | 5 | Client Dashboard
|  | 5.1 | Client Profile Tab UI + Generic Dashboard Nav | 1 | Rahul Shahi
|  | 5.2 | Client goal progress component
|  | 5.2.1 | Individual progress | 1 | Rahul Shahi
|  | 5.2.2 | Overall progress | 1 | Rahul Shahi
|  | 5.3 | Dashboard action tab setup + code splitting + Private Routing | 1 | Rahul Shahi
|  | 5.4 | Personalised Content
|  | 5.4.1 | Content Card
| Week 3 Deliverable | 5.4.1.1 | Content Thumbnail + tag pills + metadata wrapping | 3 | Rahul Shahi
|  | 5.4.1.2 | Content Card Pagination UI | 1 | Rahul Shahi
|  | 5.5 | Coach Tab UI
|  | 5.5.1 | Personal Coach Card + Calendly Integration | 3 | Rahul Sharma
|  | 5.5.2 | All Coach UI generic card | 2 | Rahul Sharma
|  | 5.6 | Goal Updates Tab UI
| Week 4 Deliverable | 5.6.1 | All goal list | 2 | Rahul Shahi
|  | 5.6.2 | Add goal form | 2 | Rahul Shahi
|  | 5.6.3 | Edit Goal form | 2 | Rahul Sharma
|  | 5.6.4 | Individual Goal Display UI | 2 | Rahul Sharma
|  | 5.6.5 | Goal Stage wizard | 1 | Rahul Sharma
|  | 6 | Coach DashBoard
|  | 6.1 | Coach routing setup + Redux coach store setup | 2 | Rahul Shahi
| Week 5 Deliverable | 6.2 | Coach Client list UI | 3 | Rahul Shahi
|  | 6.3 | Individual Client detail UI | 3 | Rahul Shahi
|  | 6.4 | Coach Client goal wizard | 2 | Rahul Sharma
|  | 6.5 | Coach meeting notes wizard | 2 | Rahul Sharma
|  | 7 | Admin Dashboard UI
| Week 6 Deliverable | 7.1 | Admin routing setup + Redux admin store setup | 1 | Rahul Sharma
|  | 7.2 | All Coach UI | 2 | Rahul Sharma
|  | 7.3 | Coach action wizard | 1 | Rahul Sharma
|  | 7.4 | All Client UI | 2 | Rahul Shahi
|  | 7.5 | Client action wizard | 1 | Rahul Shahi
| Week 7 Deliverable | 8 | Dev Testing + Bug fix | 4 | Rahul Shahi + Rahul Sharma
Amol
Abhinav
Sumantra
Rahul Shahi
Rahul Sharma

## Test Plan
Client
1 | Post signup, client gets a verify email address mail and by clicking on the verification email he is redirected to NetWorthy portal.
2 | Post verification, client gets a survey form.
3 | Post filling survey form, a client should be able to log into the portal and view the dashboard.
4 | The client should be able to edit the profile (except the disabled fields) which includes both his personal details and the survey form post signup. Upon saving the changes the profile should reflect the changes.
5 | A client is able to add a financial goal along with tags. Post adding the goal, he should see the goal stage as "not started".
6 | The client should then also be able to edit the goal. The changes should reflect when saved.
7 | The client is able to see all the coaches and their calendly schedule.
8 | The client can change the stage of all goals the client created. Once the client marks the goal as completed, it will go “in review” state until the coach approves it, post which it changes to “completed”.
9 | The client is able to choose a coach from the list of coaches.
10 | The client should have only one coach at a given time.
11 | A client can go to the coach tab and can remove his coach.
12 | A client can go to the coach tab and view all the coachs available on the platform.
13 | A client can go to the coach tab and add a new coach.
14 | The client is able to see the personalized content based on the tags of his goals.
15 | The client is not be able to view the post meeting notes added by the coach.
16 | The client upon logging out should be redirected to the login page.
Coach
1 | Post signup, the coach gets a to verify email address mail and by clicking on the verification email sent he is redirected to NetWorthy portal.
2 | Post Verfication, the coach is able to see and send the profile survey form.
3 | Post sign-up and approval by the NetWorthy admin, the coach is able to login.
4 | The coach is able to see the client goals (and its stages) including their basic contact information.
5 | The coach is able to approve his client's goal that is “in-review” and move it to “completed” state.
6 | The coach is able to request a client to schedule a follow-up meeting if they require.
7 | The coach is able to add meeting notes related to a particular goal with the meeting timestamp.
Admin
1 | Admin will have their own login page to login into NetWorthy.
2 | The admin can see the coach's personal information (including their resume, letters of reference, and their contact information) based on which the admin has the option to approve/reject a coach when the coach initially signs up on the NetWorthy Portal.
3 | The admin can remove any client or coach from the application.
4 | The admin can see information of all the coaches and the clients.